## Overview
MindoTours site plan
As of | 2026-09-19
Page pairs | 41
Language pages | 82
Critical pairs | 6
High-priority pairs | 14
Hold pairs | 4
Primary role | Broad Mindo planning and commercial funnel
Lead destination | Mindo Bird Watching operations
Implementation sequence
Phase 0 | Repair security, conversion, language pairing and missing hubs
Phase 1 | Build highest-demand commercial pages and activity clusters
Phase 2 | Expand travel planning, nature and audience guides
Phase 3 | Publish lower-priority pages only after product review
Sources
MindoTours repository | Existing HTML, includes, CSS, Functions and sitemap
MBW repository | Reusable architecture, attribution patterns and sister-site destinations
Product catalog | MBW_Accounting_System - product_catalog (4).csv
Search Console | MindoTours and MBW exports dated 2026-09-19
MBW sitemap master | MBW_SiteMap - sitemap_seo_enriched (3).csv

## Technical Audit
severity | area | finding | evidence | recommended_action | phase
Critical | Lead security | A shared server secret was embedded in public HTML and remains in repository history. | book-tour and testing pages before staging commit 5b86316 | Rotate CF_SHARED_SECRET in the receiver and every Cloudflare environment; never send it to the browser. | phase_0
Critical | Preview configuration | Preview Pages Functions cannot currently read at least one required secret. | Live POST returns booking service temporarily unavailable after redeploy | Add all three secrets to the Preview environment and redeploy. | phase_0
Critical | Turnstile | The preview widget still returns hostname error 110200. | Browser console on branch preview | Save Global Book Tour Forms after adding the preview hostname, then retest. | phase_0
Critical | Broken architecture | Core hubs are linked throughout the site but do not exist. | /tours/ has 23 references; /activities/ and /es/actividades/ are also missing | Build bilingual Tours and Activities hubs before publishing deeper pages. | phase_0
Critical | Language pairing | The Spanish birdwatching URL contains English lang, title, H1 and canonical pointing to a missing English URL. | /es/tours-de-avistamiento-de-aves-mindo/ | Build the English counterpart and rewrite the Spanish page with correct canonical and hreflang. | phase_0
Critical | Lead destination | Contact page is effectively empty. | /contact/index.html contains no usable page | Build EN/ES contact pages routed to MBW with source attribution. | phase_0
High | Homepage | Homepage remains a coming-soon splash and does not expose the planned site architecture. | Current root index | Replace it with a bilingual destination and commercial hub. | phase_0
High | Sitemap | XML sitemap contains only the homepage. | /sitemap.xml | Generate entries for every approved canonical EN/ES page with correct lastmod values. | phase_0
High | Internal links | Many current pages point to missing guide and contact URLs. | Broken targets include /mindo-travel-guide/, /es/contacto/, /mindo-birdwatching-guide/ | Create planned hubs or replace links with the appropriate MBW destination. | phase_0
High | Analytics | GA4 foundation exists, but GA4 Admin cross-domain configuration and custom dimensions still require verification. | Client linker configuration only | Configure mindotours.com and mindobirdwatching.com in GA4 Admin; register key attribution parameters. | phase_0
High | Consent | Advertising storage is denied by default and no consent interface currently updates it. | assets/js/analytics.js | Add a compliant consent interface before advertising or remarketing activation. | phase_1
High | Product truth | Several products are active operationally but still lack verified Stripe IDs. | ACT004, ACT009, ACT011, ACT015, ACT016 | Publish informational/request pages but do not expose checkout until IDs are verified. | phase_1
High | Product governance | Review-status products could be accidentally presented as bookable. | ACT018-ACT021 and duplicate ACT017 records | Keep Hold rows excluded from sitemap/navigation until catalog review is complete. | phase_1
Medium | Attribution persistence | Client attribution is stored locally and submitted with forms, but no first-party D1 session endpoint exists on MindoTours. | assets/js/analytics.js | Add a D1 or server-side session collector after the page architecture is stable. | phase_2
Medium | Reusable design | The repo has global CSS and includes but no complete cluster system for commercial, guide, activity and itinerary pages. | assets/css and page-level inline styles | Create cluster CSS files and paired templates before scaling page production. | phase_1
Medium | Testing URLs | Testing pages remain deployed, although they are now noindex. | /testing/ and /testing2/ | Remove or protect them after replacement pages are validated. | phase_2
Medium | Search demand | MindoTours has early impressions for broad Mindo, canopy, chocolate, tubing and day-trip terms but no clicks. | Search Console export dated 2026-09-19 | Prioritize hubs and verified commercial activity pages; do not create thin variations. | phase_1
Medium | Inter-site roles | MindoTours and MBW can compete if both publish equivalent specialist birding pages. | Overlapping broad and birding topics | Use MindoTours for broad planning; link specialist birding, bears and wildlife authority to MBW. | phase_1

## Page Plan
pair_id | build_phase | priority | decision | page_type | topic_cluster | language | page_path | counterpart_path | page_name | primary_keyword | counterpart_primary_keyword | search_intent | funnel_stage | product_codes | product_truth_status | primary_cta | secondary_cta | required_internal_links | sister_site_target | schema_types | css_cluster | analytics_page_type | image_direction | source_basis | implementation_notes
MT001 | phase_0 | Critical | replace_and_expand | homepage | site_foundation | en | / | /es/ | Mindo Tours | Mindo tours Ecuador | tours en Mindo Ecuador | commercial_navigation | bottom | Multiple active products | mixed_active | Explore Mindo activities | Request a custom plan | /tours/ ¦ /activities/ ¦ /mindo-day-trips/ ¦ /mindo-travel-guide/ | https://mindobirdwatching.com/ | Organization ¦ WebSite ¦ WebPage ¦ BreadcrumbList | home | homepage | Broad Mindo cloud forest, waterfall, chocolate and adventure scene | Existing homepage plus MindoTours GSC | Replace the coming-soon presentation with a complete bilingual funnel homepage.
MT001 | phase_0 | Critical | replace_and_expand | homepage | site_foundation | es | /es/ | / | Tours en Mindo | tours en Mindo Ecuador | Mindo tours Ecuador | commercial_navigation | bottom | Multiple active products | mixed_active | Explore Mindo activities | Request a custom plan | /tours/ ¦ /activities/ ¦ /mindo-day-trips/ ¦ /mindo-travel-guide/ | https://mindobirdwatching.com/ | Organization ¦ WebSite ¦ WebPage ¦ BreadcrumbList | home | homepage | Broad Mindo cloud forest, waterfall, chocolate and adventure scene | Existing homepage plus MindoTours GSC | Replace the coming-soon presentation with a complete bilingual funnel homepage.
MT002 | phase_1 | High | retain_and_improve | destination_hub | things_to_do | en | /things-to-do-in-mindo/ | /es/cosas-que-hacer-en-mindo/ | Things to Do in Mindo | things to do in Mindo | qué hacer en Mindo | informational_commercial | middle | MBW011-MBW016 ¦ ACT004 ¦ ACT011 ¦ ACT013 ¦ ACT015-ACT017 | active_and_active_pending | Compare activities | Ask for recommendations | /activities/ ¦ /tours/ ¦ /mindo-travel-guide/ ¦ /book-tour/ | https://mindobirdwatching.com/activities/ | CollectionPage ¦ ItemList ¦ FAQPage ¦ BreadcrumbList | guide | destination_hub | Collage of Mindo activities with placeholders allowed | Existing paired pages plus MBW GSC demand | Keep broad; send detailed birdwatching intent to MBW.
MT002 | phase_1 | High | retain_and_improve | destination_hub | things_to_do | es | /es/cosas-que-hacer-en-mindo/ | /things-to-do-in-mindo/ | Cosas que Hacer en Mindo | qué hacer en Mindo | things to do in Mindo | informational_commercial | middle | MBW011-MBW016 ¦ ACT004 ¦ ACT011 ¦ ACT013 ¦ ACT015-ACT017 | active_and_active_pending | Compare activities | Ask for recommendations | /activities/ ¦ /tours/ ¦ /mindo-travel-guide/ ¦ /book-tour/ | https://mindobirdwatching.com/activities/ | CollectionPage ¦ ItemList ¦ FAQPage ¦ BreadcrumbList | guide | destination_hub | Collage of Mindo activities with placeholders allowed | Existing paired pages plus MBW GSC demand | Keep broad; send detailed birdwatching intent to MBW.
MT003 | phase_0 | Critical | create_missing_hub | commercial_hub | tours | en | /tours/ | /es/tours/ | Mindo Tours and Guided Experiences | Mindo tours | tours en Mindo | commercial | middle | MBW004-MBW010 ¦ OSO001-OSO002 ¦ Multiple activities | active | View tour options | Request a private itinerary | /private-tours-mindo/ ¦ /mindo-day-trips/ ¦ /activities/ ¦ /book-tour/ | https://mindobirdwatching.com/tours/ | CollectionPage ¦ ItemList ¦ BreadcrumbList | commercial_hub | commercial_hub | Guided Mindo experience overview | Broken-link audit and product catalog | Required because 23 current internal links point to this missing hub.
MT003 | phase_0 | Critical | create_missing_hub | commercial_hub | tours | es | /es/tours/ | /tours/ | Tours y Experiencias Guiadas en Mindo | tours en Mindo | Mindo tours | commercial | middle | MBW004-MBW010 ¦ OSO001-OSO002 ¦ Multiple activities | active | View tour options | Request a private itinerary | /private-tours-mindo/ ¦ /mindo-day-trips/ ¦ /activities/ ¦ /book-tour/ | https://mindobirdwatching.com/tours/ | CollectionPage ¦ ItemList ¦ BreadcrumbList | commercial_hub | commercial_hub | Guided Mindo experience overview | Broken-link audit and product catalog | Required because 23 current internal links point to this missing hub.
MT004 | phase_0 | Critical | create_missing_hub | commercial_hub | activities | en | /activities/ | /es/actividades/ | Mindo Activities | Mindo activities | actividades en Mindo | commercial | middle | MBW011-MBW016 ¦ ACT004 ¦ ACT009-ACT017 | active_and_active_pending | Explore activities | Build a mixed itinerary | /things-to-do-in-mindo/ ¦ /tours/ ¦ /book-tour/ | https://mindobirdwatching.com/activities/ | CollectionPage ¦ ItemList ¦ BreadcrumbList | commercial_hub | commercial_hub | Activity-card grid with category imagery | Broken-link audit and product catalog | Required because current pages already link to this missing hub.
MT004 | phase_0 | Critical | create_missing_hub | commercial_hub | activities | es | /es/actividades/ | /activities/ | Actividades en Mindo | actividades en Mindo | Mindo activities | commercial | middle | MBW011-MBW016 ¦ ACT004 ¦ ACT009-ACT017 | active_and_active_pending | Explore activities | Build a mixed itinerary | /things-to-do-in-mindo/ ¦ /tours/ ¦ /book-tour/ | https://mindobirdwatching.com/activities/ | CollectionPage ¦ ItemList ¦ BreadcrumbList | commercial_hub | commercial_hub | Activity-card grid with category imagery | Broken-link audit and product catalog | Required because current pages already link to this missing hub.
MT005 | phase_0 | Critical | retain_en_create_es | lead_form | conversion | en | /book-tour/ | /es/reservar-tour/ | Book a Tour in Mindo | book Mindo tour | reservar tour en Mindo | transactional | bottom | Multiple active products | mixed_active | Send booking request | WhatsApp | /tours/ ¦ /activities/ ¦ /private-tours-mindo/ | https://mindobirdwatching.com/contact/ | WebPage ¦ ContactPage ¦ BreadcrumbList | conversion | lead_form | Friendly guide or planning consultation | Existing EN form and shared MBW lead destination | Both languages must use the same secure Pages Function and attribution fields.
MT005 | phase_0 | Critical | retain_en_create_es | lead_form | conversion | es | /es/reservar-tour/ | /book-tour/ | Reservar un Tour en Mindo | reservar tour en Mindo | book Mindo tour | transactional | bottom | Multiple active products | mixed_active | Send booking request | WhatsApp | /tours/ ¦ /activities/ ¦ /private-tours-mindo/ | https://mindobirdwatching.com/contact/ | WebPage ¦ ContactPage ¦ BreadcrumbList | conversion | lead_form | Friendly guide or planning consultation | Existing EN form and shared MBW lead destination | Both languages must use the same secure Pages Function and attribution fields.
MT006 | phase_0 | Critical | replace_empty_create_es | contact_page | conversion | en | /contact/ | /es/contacto/ | Contact Mindo Tours | contact Mindo Tours | contactar tours en Mindo | transactional | bottom | Multiple active products | mixed_active | Send an inquiry | WhatsApp | /book-tour/ ¦ /tours/ ¦ /activities/ | https://mindobirdwatching.com/contact/ | ContactPage ¦ Organization ¦ BreadcrumbList | conversion | contact_page | Simple team or cloud-forest contact visual | Current contact page is empty | Route into MBW while retaining source_site=mindotours.
MT006 | phase_0 | Critical | replace_empty_create_es | contact_page | conversion | es | /es/contacto/ | /contact/ | Contacto Mindo Tours | contactar tours en Mindo | contact Mindo Tours | transactional | bottom | Multiple active products | mixed_active | Send an inquiry | WhatsApp | /book-tour/ ¦ /tours/ ¦ /activities/ | https://mindobirdwatching.com/contact/ | ContactPage ¦ Organization ¦ BreadcrumbList | conversion | contact_page | Simple team or cloud-forest contact visual | Current contact page is empty | Route into MBW while retaining source_site=mindotours.
MT007 | phase_2 | Medium | retain_en_create_es | about_page | trust | en | /about/ | /es/sobre-nosotros/ | About Mindo Tours | Mindo local tour team | equipo local de tours Mindo | informational | top |  | not_applicable | Explore tours | Contact the team | /tours/ ¦ /things-to-do-in-mindo/ ¦ /contact/ | https://mindobirdwatching.com/about/ | AboutPage ¦ Organization ¦ BreadcrumbList | trust | about_page | Local team and destination context | Existing EN page and sister-site trust | Avoid unsupported credentials or review claims.
MT007 | phase_2 | Medium | retain_en_create_es | about_page | trust | es | /es/sobre-nosotros/ | /about/ | Sobre Mindo Tours | equipo local de tours Mindo | Mindo local tour team | informational | top |  | not_applicable | Explore tours | Contact the team | /tours/ ¦ /things-to-do-in-mindo/ ¦ /contact/ | https://mindobirdwatching.com/about/ | AboutPage ¦ Organization ¦ BreadcrumbList | trust | about_page | Local team and destination context | Existing EN page and sister-site trust | Avoid unsupported credentials or review claims.
MT008 | phase_1 | High | create_missing_hub | travel_guide_hub | travel_planning | en | /mindo-travel-guide/ | /es/guia-de-viaje-mindo/ | Mindo Travel Guide | Mindo travel guide | guía de viaje Mindo | informational | top |  | not_applicable | Plan your visit | See tours | /how-to-get-to-mindo/ ¦ /best-time-to-visit-mindo/ ¦ /things-to-do-in-mindo/ ¦ /mindo-itinerary-one-day/ | https://mindobirdwatching.com/mindo-travel-guide/ | CollectionPage ¦ ItemList ¦ BreadcrumbList | guide_hub | travel_guide_hub | Map-style Mindo planning overview | Broken-link audit and existing guide pages | Required because current pages already link to this missing guide hub.
MT008 | phase_1 | High | create_missing_hub | travel_guide_hub | travel_planning | es | /es/guia-de-viaje-mindo/ | /mindo-travel-guide/ | Guía de Viaje de Mindo | guía de viaje Mindo | Mindo travel guide | informational | top |  | not_applicable | Plan your visit | See tours | /how-to-get-to-mindo/ ¦ /best-time-to-visit-mindo/ ¦ /things-to-do-in-mindo/ ¦ /mindo-itinerary-one-day/ | https://mindobirdwatching.com/mindo-travel-guide/ | CollectionPage ¦ ItemList ¦ BreadcrumbList | guide_hub | travel_guide_hub | Map-style Mindo planning overview | Broken-link audit and existing guide pages | Required because current pages already link to this missing guide hub.
MT009 | phase_1 | High | retain_and_improve | commercial_guide | day_trips | en | /mindo-day-trips/ | /es/excursiones-de-un-dia-mindo/ | Mindo Day Trips | Mindo day trip from Quito | tour a Mindo desde Quito | commercial | middle | TRANS03 ¦ TRANS06 ¦ Multiple activities | active_mixed_checkout | Compare day-trip options | Request a custom day | /quito-to-mindo-transport/ ¦ /things-to-do-in-mindo/ ¦ /private-tours-mindo/ ¦ /book-tour/ | https://mindobirdwatching.com/mindo-day-tour-from-quito/ | TouristTrip ¦ FAQPage ¦ BreadcrumbList | commercial_guide | commercial_guide | Quito-to-Mindo day-trip journey | Existing paired pages and MBW GSC demand | Clarify inclusions and do not imply transport is included unless selected.
MT009 | phase_1 | High | retain_and_improve | commercial_guide | day_trips | es | /es/excursiones-de-un-dia-mindo/ | /mindo-day-trips/ | Excursiones de un Día a Mindo | tour a Mindo desde Quito | Mindo day trip from Quito | commercial | middle | TRANS03 ¦ TRANS06 ¦ Multiple activities | active_mixed_checkout | Compare day-trip options | Request a custom day | /quito-to-mindo-transport/ ¦ /things-to-do-in-mindo/ ¦ /private-tours-mindo/ ¦ /book-tour/ | https://mindobirdwatching.com/mindo-day-tour-from-quito/ | TouristTrip ¦ FAQPage ¦ BreadcrumbList | commercial_guide | commercial_guide | Quito-to-Mindo day-trip journey | Existing paired pages and MBW GSC demand | Clarify inclusions and do not imply transport is included unless selected.
MT010 | phase_1 | High | retain_and_improve | commercial_page | private_tours | en | /private-tours-mindo/ | /es/tours-privados-mindo/ | Private Tours in Mindo | private tours Mindo | tours privados Mindo | commercial | bottom | MBW007 ¦ MBW008 | active | Request a private tour | Compare tour ideas | /tours/ ¦ /mindo-day-trips/ ¦ /book-tour/ | https://mindobirdwatching.com/tours/custom-private-tour/ | TouristTrip ¦ Service ¦ FAQPage ¦ BreadcrumbList | commercial | commercial_page | Private guide with flexible group | Existing paired pages and active custom products | Keep pricing conditional on scope and group.
MT010 | phase_1 | High | retain_and_improve | commercial_page | private_tours | es | /es/tours-privados-mindo/ | /private-tours-mindo/ | Tours Privados en Mindo | tours privados Mindo | private tours Mindo | commercial | bottom | MBW007 ¦ MBW008 | active | Request a private tour | Compare tour ideas | /tours/ ¦ /mindo-day-trips/ ¦ /book-tour/ | https://mindobirdwatching.com/tours/custom-private-tour/ | TouristTrip ¦ Service ¦ FAQPage ¦ BreadcrumbList | commercial | commercial_page | Private guide with flexible group | Existing paired pages and active custom products | Keep pricing conditional on scope and group.
MT011 | phase_1 | High | retain_and_improve | travel_guide | transport | en | /how-to-get-to-mindo/ | /es/como-llegar-a-mindo/ | How to Get to Mindo | how to get to Mindo from Quito | cómo llegar a Mindo desde Quito | informational_commercial | middle | TRANS01-TRANS06 | active_mixed_checkout | View private transfers | Plan a day trip | /quito-to-mindo-transport/ ¦ /mindo-day-trips/ ¦ /mindo-travel-guide/ | https://mindobirdwatching.com/how-to-get-to-mindo/ | HowTo ¦ FAQPage ¦ BreadcrumbList | guide | travel_guide | Road map or transfer vehicle placeholder | Existing paired pages and GSC queries | Verify current bus details before publication; avoid time-sensitive claims without sources.
MT011 | phase_1 | High | retain_and_improve | travel_guide | transport | es | /es/como-llegar-a-mindo/ | /how-to-get-to-mindo/ | Cómo Llegar a Mindo | cómo llegar a Mindo desde Quito | how to get to Mindo from Quito | informational_commercial | middle | TRANS01-TRANS06 | active_mixed_checkout | View private transfers | Plan a day trip | /quito-to-mindo-transport/ ¦ /mindo-day-trips/ ¦ /mindo-travel-guide/ | https://mindobirdwatching.com/how-to-get-to-mindo/ | HowTo ¦ FAQPage ¦ BreadcrumbList | guide | travel_guide | Road map or transfer vehicle placeholder | Existing paired pages and GSC queries | Verify current bus details before publication; avoid time-sensitive claims without sources.
MT012 | phase_2 | Medium | retain_and_improve | travel_guide | travel_planning | en | /best-time-to-visit-mindo/ | /es/mejor-epoca-para-visitar-mindo/ | Best Time to Visit Mindo | best time to visit Mindo | mejor época para visitar Mindo | informational | top |  | not_applicable | Plan by interest | See activities | /mindo-travel-guide/ ¦ /things-to-do-in-mindo/ ¦ /mindo-cloud-forest-guide/ | https://mindobirdwatching.com/best-time-to-visit-mindo/ | Article ¦ FAQPage ¦ BreadcrumbList | guide | travel_guide | Seasonal cloud forest without misleading weather guarantees | Existing paired pages and MBW GSC | Separate typical patterns from guarantees.
MT012 | phase_2 | Medium | retain_and_improve | travel_guide | travel_planning | es | /es/mejor-epoca-para-visitar-mindo/ | /best-time-to-visit-mindo/ | Mejor Época para Visitar Mindo | mejor época para visitar Mindo | best time to visit Mindo | informational | top |  | not_applicable | Plan by interest | See activities | /mindo-travel-guide/ ¦ /things-to-do-in-mindo/ ¦ /mindo-cloud-forest-guide/ | https://mindobirdwatching.com/best-time-to-visit-mindo/ | Article ¦ FAQPage ¦ BreadcrumbList | guide | travel_guide | Seasonal cloud forest without misleading weather guarantees | Existing paired pages and MBW GSC | Separate typical patterns from guarantees.
MT013 | phase_2 | Medium | retain_and_improve | destination_guide | cloud_forest | en | /mindo-cloud-forest-guide/ | /es/bosque-nublado-de-mindo-guia/ | Mindo Cloud Forest Guide | Mindo cloud forest | bosque nublado de Mindo | informational | top | MBW009 ¦ MBW015-MBW016 | active | Explore nature activities | Plan a guided day | /activities/ ¦ /mindo-travel-guide/ ¦ /mindo-wildlife-nature-tours/ | https://mindobirdwatching.com/mindo-cloud-forest-guide/ | Article ¦ FAQPage ¦ BreadcrumbList | guide | destination_guide | Mindo cloud forest landscape | Existing paired pages and GSC demand | Use original wording and link specialized species content to MBW.
MT013 | phase_2 | Medium | retain_and_improve | destination_guide | cloud_forest | es | /es/bosque-nublado-de-mindo-guia/ | /mindo-cloud-forest-guide/ | Guía del Bosque Nublado de Mindo | bosque nublado de Mindo | Mindo cloud forest | informational | top | MBW009 ¦ MBW015-MBW016 | active | Explore nature activities | Plan a guided day | /activities/ ¦ /mindo-travel-guide/ ¦ /mindo-wildlife-nature-tours/ | https://mindobirdwatching.com/mindo-cloud-forest-guide/ | Article ¦ FAQPage ¦ BreadcrumbList | guide | destination_guide | Mindo cloud forest landscape | Existing paired pages and GSC demand | Use original wording and link specialized species content to MBW.
MT014 | phase_0 | Critical | create_en_repair_es | sister_site_funnel | birdwatching | en | /bird-watching-tours-mindo/ | /es/tours-de-avistamiento-de-aves-mindo/ | Bird Watching Tours in Mindo | bird watching tours Mindo | tours de avistamiento de aves Mindo | commercial | bottom | MBW004-MBW010 | active | View birding tours on MBW | Ask for a mixed itinerary | /tours/ ¦ /private-tours-mindo/ ¦ /things-to-do-in-mindo/ | https://mindobirdwatching.com/tours/ | Service ¦ ItemList ¦ FAQPage ¦ BreadcrumbList | sister_funnel | sister_site_funnel | Birding guide and cloud-forest birds | Current ES file has EN metadata and missing EN counterpart | MindoTours provides the overview; MBW owns product depth and booking authority.
MT014 | phase_0 | Critical | create_en_repair_es | sister_site_funnel | birdwatching | es | /es/tours-de-avistamiento-de-aves-mindo/ | /bird-watching-tours-mindo/ | Tours de Avistamiento de Aves en Mindo | tours de avistamiento de aves Mindo | bird watching tours Mindo | commercial | bottom | MBW004-MBW010 | active | View birding tours on MBW | Ask for a mixed itinerary | /tours/ ¦ /private-tours-mindo/ ¦ /things-to-do-in-mindo/ | https://mindobirdwatching.com/tours/ | Service ¦ ItemList ¦ FAQPage ¦ BreadcrumbList | sister_funnel | sister_site_funnel | Birding guide and cloud-forest birds | Current ES file has EN metadata and missing EN counterpart | MindoTours provides the overview; MBW owns product depth and booking authority.
MT015 | phase_1 | High | create | activity_page | food_culture | en | /activities/chocolate-tour-mindo/ | /es/actividades/tour-de-chocolate-mindo/ | Chocolate Tour in Mindo | chocolate tour Mindo | tour del chocolate Mindo | commercial | bottom | MBW011 | active_checkout | Check availability | Build a mixed day | /activities/ ¦ /things-to-do-in-mindo/ ¦ /mindo-itinerary-one-day/ | https://mindobirdwatching.com/activities/ | Product ¦ TouristAttraction ¦ FAQPage ¦ BreadcrumbList | activity | activity_page | Cacao and chocolate-making experience | Product catalog and GSC queries | Use catalog price only when product pricing rules allow it.
MT015 | phase_1 | High | create | activity_page | food_culture | es | /es/actividades/tour-de-chocolate-mindo/ | /activities/chocolate-tour-mindo/ | Tour de Chocolate en Mindo | tour del chocolate Mindo | chocolate tour Mindo | commercial | bottom | MBW011 | active_checkout | Check availability | Build a mixed day | /activities/ ¦ /things-to-do-in-mindo/ ¦ /mindo-itinerary-one-day/ | https://mindobirdwatching.com/activities/ | Product ¦ TouristAttraction ¦ FAQPage ¦ BreadcrumbList | activity | activity_page | Cacao and chocolate-making experience | Product catalog and GSC queries | Use catalog price only when product pricing rules allow it.
MT016 | phase_2 | Medium | create | activity_page | food_culture | en | /activities/coffee-tour-mindo/ | /es/actividades/tour-de-cafe-mindo/ | Coffee Tour in Mindo | coffee tour Mindo | tour de café Mindo | commercial | bottom | MBW012 | active_checkout | Check availability | Compare chocolate tours | /activities/ ¦ /activities/chocolate-tour-mindo/ ¦ /mindo-itinerary-one-day/ | https://mindobirdwatching.com/activities/ | Product ¦ TouristAttraction ¦ FAQPage ¦ BreadcrumbList | activity | activity_page | Coffee plants and local preparation | Product catalog | Do not invent farm names or production methods.
MT016 | phase_2 | Medium | create | activity_page | food_culture | es | /es/actividades/tour-de-cafe-mindo/ | /activities/coffee-tour-mindo/ | Tour de Café en Mindo | tour de café Mindo | coffee tour Mindo | commercial | bottom | MBW012 | active_checkout | Check availability | Compare chocolate tours | /activities/ ¦ /activities/chocolate-tour-mindo/ ¦ /mindo-itinerary-one-day/ | https://mindobirdwatching.com/activities/ | Product ¦ TouristAttraction ¦ FAQPage ¦ BreadcrumbList | activity | activity_page | Coffee plants and local preparation | Product catalog | Do not invent farm names or production methods.
MT017 | phase_1 | High | create | activity_page | waterfalls | en | /activities/mindo-waterfall-hike/ | /es/actividades/cascadas-de-mindo/ | Mindo Waterfall Hike | Mindo waterfall tour | ruta de las cascadas Mindo | commercial | bottom | MBW013 | active_checkout | Check availability | See day-trip plans | /activities/ ¦ /activities/mindo-tarabita-cable-car/ ¦ /mindo-day-trips/ | https://mindobirdwatching.com/activities/ | Product ¦ TouristAttraction ¦ FAQPage ¦ BreadcrumbList | activity | activity_page | Waterfall trail and forest walkway | Product catalog and MBW GSC | Differentiate guided product from independent waterfall entrance information.
MT017 | phase_1 | High | create | activity_page | waterfalls | es | /es/actividades/cascadas-de-mindo/ | /activities/mindo-waterfall-hike/ | Tour de Cascadas de Mindo | ruta de las cascadas Mindo | Mindo waterfall tour | commercial | bottom | MBW013 | active_checkout | Check availability | See day-trip plans | /activities/ ¦ /activities/mindo-tarabita-cable-car/ ¦ /mindo-day-trips/ | https://mindobirdwatching.com/activities/ | Product ¦ TouristAttraction ¦ FAQPage ¦ BreadcrumbList | activity | activity_page | Waterfall trail and forest walkway | Product catalog and MBW GSC | Differentiate guided product from independent waterfall entrance information.
MT018 | phase_1 | High | create | activity_page | adventure | en | /activities/ziplining-mindo/ | /es/actividades/canopy-en-mindo/ | Ziplining and Canopy in Mindo | Mindo ziplining | canopy Mindo | commercial | bottom | MBW014 | active_checkout | Check availability | Compare adventures | /mindo-adventure-tours/ ¦ /activities/ ¦ /things-to-do-in-mindo/ | https://mindobirdwatching.com/activities/ | Product ¦ TouristAttraction ¦ FAQPage ¦ BreadcrumbList | activity_adventure | activity_page | Zipline over cloud-forest canopy | Product catalog and MindoTours GSC | Avoid unsupported claims about number or length of lines.
MT018 | phase_1 | High | create | activity_page | adventure | es | /es/actividades/canopy-en-mindo/ | /activities/ziplining-mindo/ | Canopy y Tirolina en Mindo | canopy Mindo | Mindo ziplining | commercial | bottom | MBW014 | active_checkout | Check availability | Compare adventures | /mindo-adventure-tours/ ¦ /activities/ ¦ /things-to-do-in-mindo/ | https://mindobirdwatching.com/activities/ | Product ¦ TouristAttraction ¦ FAQPage ¦ BreadcrumbList | activity_adventure | activity_page | Zipline over cloud-forest canopy | Product catalog and MindoTours GSC | Avoid unsupported claims about number or length of lines.
MT019 | phase_1 | High | create | activity_page | adventure | en | /activities/tubing-mindo/ | /es/actividades/tubing-en-mindo/ | Tubing in Mindo | tubing Mindo | tubing en Mindo | commercial | bottom | ACT011 | active_pending_stripe_ids | Request availability | Compare adventures | /mindo-adventure-tours/ ¦ /activities/canyoning-mindo/ ¦ /activities/ | https://mindobirdwatching.com/activities/tubing/ | Product ¦ TouristAttraction ¦ FAQPage ¦ BreadcrumbList | activity_adventure | activity_page | Mindo River tubing with safety gear | Product catalog and MBW GSC | Publishable product content; checkout implementation waits for verified Stripe IDs.
MT019 | phase_1 | High | create | activity_page | adventure | es | /es/actividades/tubing-en-mindo/ | /activities/tubing-mindo/ | Tubing en Mindo | tubing en Mindo | tubing Mindo | commercial | bottom | ACT011 | active_pending_stripe_ids | Request availability | Compare adventures | /mindo-adventure-tours/ ¦ /activities/canyoning-mindo/ ¦ /activities/ | https://mindobirdwatching.com/activities/tubing/ | Product ¦ TouristAttraction ¦ FAQPage ¦ BreadcrumbList | activity_adventure | activity_page | Mindo River tubing with safety gear | Product catalog and MBW GSC | Publishable product content; checkout implementation waits for verified Stripe IDs.
MT020 | phase_1 | High | create | activity_page | adventure | en | /activities/canyoning-mindo/ | /es/actividades/canyoning-en-mindo/ | Canyoning in Mindo | canyoning Mindo | canyoning en Mindo | commercial | bottom | ACT013 | active_checkout | Check availability | Compare adventures | /mindo-adventure-tours/ ¦ /activities/tubing-mindo/ ¦ /activities/ | https://mindobirdwatching.com/activities/canyoning/ | Product ¦ TouristAttraction ¦ FAQPage ¦ BreadcrumbList | activity_adventure | activity_page | Guided canyoning and waterfall descent | Product catalog and MBW GSC | State difficulty and inclusions only from verified product data.
MT020 | phase_1 | High | create | activity_page | adventure | es | /es/actividades/canyoning-en-mindo/ | /activities/canyoning-mindo/ | Canyoning en Mindo | canyoning en Mindo | canyoning Mindo | commercial | bottom | ACT013 | active_checkout | Check availability | Compare adventures | /mindo-adventure-tours/ ¦ /activities/tubing-mindo/ ¦ /activities/ | https://mindobirdwatching.com/activities/canyoning/ | Product ¦ TouristAttraction ¦ FAQPage ¦ BreadcrumbList | activity_adventure | activity_page | Guided canyoning and waterfall descent | Product catalog and MBW GSC | State difficulty and inclusions only from verified product data.
MT021 | phase_2 | Medium | create | activity_page | adventure | en | /activities/quad-tour-mindo/ | /es/actividades/tour-en-quad-mindo/ | Quad Tour in Mindo | quad tour Mindo | tour en cuadrones Mindo | commercial | bottom | ACT004 | active_pending_stripe_ids | Request availability | Compare adventures | /mindo-adventure-tours/ ¦ /activities/ ¦ /private-tours-mindo/ | https://mindobirdwatching.com/activities/quad-tour/ | Product ¦ TouristAttraction ¦ FAQPage ¦ BreadcrumbList | activity_adventure | activity_page | Quad route with mountain scenery | Product catalog | Use request flow until Stripe IDs are verified.
MT021 | phase_2 | Medium | create | activity_page | adventure | es | /es/actividades/tour-en-quad-mindo/ | /activities/quad-tour-mindo/ | Tour en Quad en Mindo | tour en cuadrones Mindo | quad tour Mindo | commercial | bottom | ACT004 | active_pending_stripe_ids | Request availability | Compare adventures | /mindo-adventure-tours/ ¦ /activities/ ¦ /private-tours-mindo/ | https://mindobirdwatching.com/activities/quad-tour/ | Product ¦ TouristAttraction ¦ FAQPage ¦ BreadcrumbList | activity_adventure | activity_page | Quad route with mountain scenery | Product catalog | Use request flow until Stripe IDs are verified.
MT022 | phase_2 | Medium | create | activity_page | gardens | en | /activities/orchid-garden-mindo/ | /es/actividades/jardin-de-orquideas-mindo/ | Orchid Garden Tour in Mindo | Mindo orchid garden | jardín de orquídeas Mindo | commercial | middle | ACT009 | active_pending_stripe_ids | Request availability | Explore nature activities | /mindo-wildlife-nature-tours/ ¦ /activities/ ¦ /mindo-cloud-forest-guide/ | https://mindobirdwatching.com/activities/orchid-garden-tour/ | Product ¦ TouristAttraction ¦ FAQPage ¦ BreadcrumbList | activity_nature | activity_page | Macro orchid detail with garden context | Product catalog | Use request flow until Stripe IDs are verified.
MT022 | phase_2 | Medium | create | activity_page | gardens | es | /es/actividades/jardin-de-orquideas-mindo/ | /activities/orchid-garden-mindo/ | Tour del Jardín de Orquídeas en Mindo | jardín de orquídeas Mindo | Mindo orchid garden | commercial | middle | ACT009 | active_pending_stripe_ids | Request availability | Explore nature activities | /mindo-wildlife-nature-tours/ ¦ /activities/ ¦ /mindo-cloud-forest-guide/ | https://mindobirdwatching.com/activities/orchid-garden-tour/ | Product ¦ TouristAttraction ¦ FAQPage ¦ BreadcrumbList | activity_nature | activity_page | Macro orchid detail with garden context | Product catalog | Use request flow until Stripe IDs are verified.
MT023 | phase_2 | Medium | create | activity_page | gardens | en | /activities/butterfly-garden-mindo/ | /es/actividades/mariposario-mindo/ | Butterfly Garden in Mindo | Mindo butterfly garden | mariposario Mindo | commercial | middle | MBW015 | active_checkout | Check availability | Explore family activities | /family-things-to-do-mindo/ ¦ /activities/ ¦ /mindo-wildlife-nature-tours/ | https://mindobirdwatching.com/activities/ | Product ¦ TouristAttraction ¦ FAQPage ¦ BreadcrumbList | activity_nature | activity_page | Butterflies in a garden habitat | Product catalog | Avoid guarantees about species present on a visit.
MT023 | phase_2 | Medium | create | activity_page | gardens | es | /es/actividades/mariposario-mindo/ | /activities/butterfly-garden-mindo/ | Mariposario de Mindo | mariposario Mindo | Mindo butterfly garden | commercial | middle | MBW015 | active_checkout | Check availability | Explore family activities | /family-things-to-do-mindo/ ¦ /activities/ ¦ /mindo-wildlife-nature-tours/ | https://mindobirdwatching.com/activities/ | Product ¦ TouristAttraction ¦ FAQPage ¦ BreadcrumbList | activity_nature | activity_page | Butterflies in a garden habitat | Product catalog | Avoid guarantees about species present on a visit.
MT024 | phase_1 | High | create | activity_page | wildlife | en | /activities/night-walk-mindo/ | /es/actividades/caminata-nocturna-mindo/ | Night Walk in Mindo | Mindo night walk | caminata nocturna Mindo | commercial | bottom | MBW016 | active_checkout | Check availability | See wildlife tours | /mindo-wildlife-nature-tours/ ¦ /activities/frog-concert-mindo/ ¦ /activities/ | https://mindobirdwatching.com/mindo-night-walk/ | Product ¦ TouristAttraction ¦ FAQPage ¦ BreadcrumbList | activity_wildlife | activity_page | Guide with flashlight and nocturnal forest | Product catalog and MBW GSC | MBW owns detailed specialist content; MindoTours provides broad trip-planning context.
MT024 | phase_1 | High | create | activity_page | wildlife | es | /es/actividades/caminata-nocturna-mindo/ | /activities/night-walk-mindo/ | Caminata Nocturna en Mindo | caminata nocturna Mindo | Mindo night walk | commercial | bottom | MBW016 | active_checkout | Check availability | See wildlife tours | /mindo-wildlife-nature-tours/ ¦ /activities/frog-concert-mindo/ ¦ /activities/ | https://mindobirdwatching.com/mindo-night-walk/ | Product ¦ TouristAttraction ¦ FAQPage ¦ BreadcrumbList | activity_wildlife | activity_page | Guide with flashlight and nocturnal forest | Product catalog and MBW GSC | MBW owns detailed specialist content; MindoTours provides broad trip-planning context.
MT025 | phase_2 | Medium | create | activity_page | nature | en | /activities/horseback-riding-mindo/ | /es/actividades/paseo-a-caballo-mindo/ | Horseback Riding in Mindo | horseback riding Mindo | paseo a caballo Mindo | commercial | bottom | ACT016 | active_pending_stripe_ids | Request availability | Compare nature activities | /activities/ ¦ /private-tours-mindo/ ¦ /things-to-do-in-mindo/ | https://mindobirdwatching.com/activities/ | Product ¦ TouristAttraction ¦ FAQPage ¦ BreadcrumbList | activity_nature | activity_page | Horseback route in green Mindo landscape | Product catalog | Confirm route and operating details before final publication.
MT025 | phase_2 | Medium | create | activity_page | nature | es | /es/actividades/paseo-a-caballo-mindo/ | /activities/horseback-riding-mindo/ | Paseo a Caballo en Mindo | paseo a caballo Mindo | horseback riding Mindo | commercial | bottom | ACT016 | active_pending_stripe_ids | Request availability | Compare nature activities | /activities/ ¦ /private-tours-mindo/ ¦ /things-to-do-in-mindo/ | https://mindobirdwatching.com/activities/ | Product ¦ TouristAttraction ¦ FAQPage ¦ BreadcrumbList | activity_nature | activity_page | Horseback route in green Mindo landscape | Product catalog | Confirm route and operating details before final publication.
MT026 | phase_2 | Medium | create | activity_page | adventure | en | /activities/mountain-biking-mindo/ | /es/actividades/ciclismo-de-montana-mindo/ | Mountain Biking in Mindo | mountain biking Mindo | ciclismo de montaña Mindo | commercial | bottom | ACT017 | active_checkout | Check availability | Compare adventures | /mindo-adventure-tours/ ¦ /activities/ ¦ /private-tours-mindo/ | https://mindobirdwatching.com/activities/mountain-biking/ | Product ¦ TouristAttraction ¦ FAQPage ¦ BreadcrumbList | activity_adventure | activity_page | Mountain bike on a cloud-forest road | Product catalog | Route-dependent duration; avoid fixed route claims.
MT026 | phase_2 | Medium | create | activity_page | adventure | es | /es/actividades/ciclismo-de-montana-mindo/ | /activities/mountain-biking-mindo/ | Ciclismo de Montaña en Mindo | ciclismo de montaña Mindo | mountain biking Mindo | commercial | bottom | ACT017 | active_checkout | Check availability | Compare adventures | /mindo-adventure-tours/ ¦ /activities/ ¦ /private-tours-mindo/ | https://mindobirdwatching.com/activities/mountain-biking/ | Product ¦ TouristAttraction ¦ FAQPage ¦ BreadcrumbList | activity_adventure | activity_page | Mountain bike on a cloud-forest road | Product catalog | Route-dependent duration; avoid fixed route claims.
MT027 | phase_2 | Medium | create | activity_page | wildlife | en | /activities/frog-concert-mindo/ | /es/actividades/concierto-de-ranas-mindo/ | Frog Concert in Mindo | Mindo frog concert | concierto de ranas Mindo | commercial | middle | ACT010 | active_checkout_ids_pending_review | Check availability | Compare night activities | /activities/night-walk-mindo/ ¦ /mindo-wildlife-nature-tours/ ¦ /activities/ | https://mindobirdwatching.com/activities/ | Product ¦ TouristAttraction ¦ FAQPage ¦ BreadcrumbList | activity_wildlife | activity_page | Frog habitat at dusk | Product catalog | Do not guarantee frog activity or specific sightings.
MT027 | phase_2 | Medium | create | activity_page | wildlife | es | /es/actividades/concierto-de-ranas-mindo/ | /activities/frog-concert-mindo/ | Concierto de Ranas en Mindo | concierto de ranas Mindo | Mindo frog concert | commercial | middle | ACT010 | active_checkout_ids_pending_review | Check availability | Compare night activities | /activities/night-walk-mindo/ ¦ /mindo-wildlife-nature-tours/ ¦ /activities/ | https://mindobirdwatching.com/activities/ | Product ¦ TouristAttraction ¦ FAQPage ¦ BreadcrumbList | activity_wildlife | activity_page | Frog habitat at dusk | Product catalog | Do not guarantee frog activity or specific sightings.
MT028 | phase_3 | Low | create | activity_page | flora | en | /activities/flora-tour-mindo/ | /es/actividades/tour-de-flora-mindo/ | Flora Tour in Mindo | Mindo flora tour | tour de flora Mindo | commercial | middle | MBW009 | active_checkout | Check availability | Explore nature tours | /mindo-wildlife-nature-tours/ ¦ /activities/orchid-garden-mindo/ ¦ /activities/ | https://mindobirdwatching.com/activities/ | Product ¦ TouristAttraction ¦ FAQPage ¦ BreadcrumbList | activity_nature | activity_page | Botanical guide with cloud-forest plants | Product catalog | Use botanical claims only when verified.
MT028 | phase_3 | Low | create | activity_page | flora | es | /es/actividades/tour-de-flora-mindo/ | /activities/flora-tour-mindo/ | Tour de Flora en Mindo | tour de flora Mindo | Mindo flora tour | commercial | middle | MBW009 | active_checkout | Check availability | Explore nature tours | /mindo-wildlife-nature-tours/ ¦ /activities/orchid-garden-mindo/ ¦ /activities/ | https://mindobirdwatching.com/activities/ | Product ¦ TouristAttraction ¦ FAQPage ¦ BreadcrumbList | activity_nature | activity_page | Botanical guide with cloud-forest plants | Product catalog | Use botanical claims only when verified.
MT029 | phase_3 | Low | create | activity_page | adventure | en | /activities/paintball-mindo/ | /es/actividades/paintball-mindo/ | Paintball in Mindo | paintball Mindo | paintball Mindo | commercial | bottom | ACT015 | active_pending_stripe_ids | Request availability | Compare group activities | /mindo-adventure-tours/ ¦ /family-things-to-do-mindo/ ¦ /activities/ | https://mindobirdwatching.com/activities/paintball/ | Product ¦ TouristAttraction ¦ FAQPage ¦ BreadcrumbList | activity_adventure | activity_page | Outdoor paintball course | Product catalog | Use request flow until Stripe IDs and operating details are verified.
MT029 | phase_3 | Low | create | activity_page | adventure | es | /es/actividades/paintball-mindo/ | /activities/paintball-mindo/ | Paintball en Mindo | paintball Mindo | paintball Mindo | commercial | bottom | ACT015 | active_pending_stripe_ids | Request availability | Compare group activities | /mindo-adventure-tours/ ¦ /family-things-to-do-mindo/ ¦ /activities/ | https://mindobirdwatching.com/activities/paintball/ | Product ¦ TouristAttraction ¦ FAQPage ¦ BreadcrumbList | activity_adventure | activity_page | Outdoor paintball course | Product catalog | Use request flow until Stripe IDs and operating details are verified.
MT030 | phase_1 | High | create | sister_site_funnel | bears | en | /spectacled-bear-tours-ecuador/ | /es/tours-de-oso-de-anteojos-ecuador/ | Spectacled Bear Tours in Ecuador | spectacled bear tour Ecuador | tour oso de anteojos Ecuador | commercial | bottom | OSO001 ¦ OSO002 | active_checkout | View bear tours on MBW | Ask about conditions | /mindo-wildlife-nature-tours/ ¦ /private-tours-mindo/ ¦ /tours/ | https://mindobirdwatching.com/tours/spectacled-bear-tour-ecuador/ | Service ¦ ItemList ¦ FAQPage ¦ BreadcrumbList | sister_funnel | sister_site_funnel | Spectacled bear habitat with no sighting guarantee | Product catalog and MBW GSC | State clearly that wildlife sightings depend on conditions; MBW owns booking detail.
MT030 | phase_1 | High | create | sister_site_funnel | bears | es | /es/tours-de-oso-de-anteojos-ecuador/ | /spectacled-bear-tours-ecuador/ | Tours del Oso de Anteojos en Ecuador | tour oso de anteojos Ecuador | spectacled bear tour Ecuador | commercial | bottom | OSO001 ¦ OSO002 | active_checkout | View bear tours on MBW | Ask about conditions | /mindo-wildlife-nature-tours/ ¦ /private-tours-mindo/ ¦ /tours/ | https://mindobirdwatching.com/tours/spectacled-bear-tour-ecuador/ | Service ¦ ItemList ¦ FAQPage ¦ BreadcrumbList | sister_funnel | sister_site_funnel | Spectacled bear habitat with no sighting guarantee | Product catalog and MBW GSC | State clearly that wildlife sightings depend on conditions; MBW owns booking detail.
MT031 | phase_1 | High | create | transport_page | transport | en | /quito-to-mindo-transport/ | /es/transporte-quito-a-mindo/ | Quito to Mindo Private Transport | Quito to Mindo private transfer | transporte privado Quito Mindo | commercial | bottom | TRANS01 ¦ TRANS02 ¦ TRANS03 ¦ TRANS04 ¦ TRANS06 | active_mixed_checkout | Request transport | See day trips | /how-to-get-to-mindo/ ¦ /mindo-day-trips/ ¦ /book-tour/ | https://mindobirdwatching.com/contact/ | Service ¦ FAQPage ¦ BreadcrumbList | transport | transport_page | Private vehicle on the Quito-Mindo route | Product catalog and GSC | Do not show a single universal price across route variants.
MT031 | phase_1 | High | create | transport_page | transport | es | /es/transporte-quito-a-mindo/ | /quito-to-mindo-transport/ | Transporte Privado de Quito a Mindo | transporte privado Quito Mindo | Quito to Mindo private transfer | commercial | bottom | TRANS01 ¦ TRANS02 ¦ TRANS03 ¦ TRANS04 ¦ TRANS06 | active_mixed_checkout | Request transport | See day trips | /how-to-get-to-mindo/ ¦ /mindo-day-trips/ ¦ /book-tour/ | https://mindobirdwatching.com/contact/ | Service ¦ FAQPage ¦ BreadcrumbList | transport | transport_page | Private vehicle on the Quito-Mindo route | Product catalog and GSC | Do not show a single universal price across route variants.
MT032 | phase_1 | High | create | commercial_hub | adventure | en | /mindo-adventure-tours/ | /es/tours-de-aventura-mindo/ | Mindo Adventure Tours | Mindo adventure tours | tours de aventura Mindo | commercial | middle | MBW014 ¦ ACT004 ¦ ACT011 ¦ ACT013 ¦ ACT015 ¦ ACT017 | active_and_active_pending | Compare adventures | Request a custom day | /activities/ziplining-mindo/ ¦ /activities/tubing-mindo/ ¦ /activities/canyoning-mindo/ ¦ /activities/mountain-biking-mindo/ | https://mindobirdwatching.com/activities/ | CollectionPage ¦ ItemList ¦ FAQPage ¦ BreadcrumbList | commercial_hub | commercial_hub | Adventure collage with zipline, river and bike | Product catalog and MindoTours GSC | Exclude rafting as an active product.
MT032 | phase_1 | High | create | commercial_hub | adventure | es | /es/tours-de-aventura-mindo/ | /mindo-adventure-tours/ | Tours de Aventura en Mindo | tours de aventura Mindo | Mindo adventure tours | commercial | middle | MBW014 ¦ ACT004 ¦ ACT011 ¦ ACT013 ¦ ACT015 ¦ ACT017 | active_and_active_pending | Compare adventures | Request a custom day | /activities/ziplining-mindo/ ¦ /activities/tubing-mindo/ ¦ /activities/canyoning-mindo/ ¦ /activities/mountain-biking-mindo/ | https://mindobirdwatching.com/activities/ | CollectionPage ¦ ItemList ¦ FAQPage ¦ BreadcrumbList | commercial_hub | commercial_hub | Adventure collage with zipline, river and bike | Product catalog and MindoTours GSC | Exclude rafting as an active product.
MT033 | phase_2 | Medium | create | commercial_hub | wildlife_nature | en | /mindo-wildlife-nature-tours/ | /es/tours-de-naturaleza-y-fauna-mindo/ | Mindo Wildlife and Nature Tours | Mindo wildlife tours | tours de naturaleza Mindo | commercial | middle | MBW009 ¦ MBW015-MBW016 ¦ ACT009-ACT010 ¦ OSO001-OSO002 | active_and_active_pending | Explore nature tours | Request a custom plan | /activities/night-walk-mindo/ ¦ /activities/orchid-garden-mindo/ ¦ /spectacled-bear-tours-ecuador/ | https://mindobirdwatching.com/ | CollectionPage ¦ ItemList ¦ FAQPage ¦ BreadcrumbList | commercial_hub | commercial_hub | Cloud-forest wildlife without guaranteed sightings | Product catalog | Link specialist birding and bear content to MBW.
MT033 | phase_2 | Medium | create | commercial_hub | wildlife_nature | es | /es/tours-de-naturaleza-y-fauna-mindo/ | /mindo-wildlife-nature-tours/ | Tours de Naturaleza y Fauna en Mindo | tours de naturaleza Mindo | Mindo wildlife tours | commercial | middle | MBW009 ¦ MBW015-MBW016 ¦ ACT009-ACT010 ¦ OSO001-OSO002 | active_and_active_pending | Explore nature tours | Request a custom plan | /activities/night-walk-mindo/ ¦ /activities/orchid-garden-mindo/ ¦ /spectacled-bear-tours-ecuador/ | https://mindobirdwatching.com/ | CollectionPage ¦ ItemList ¦ FAQPage ¦ BreadcrumbList | commercial_hub | commercial_hub | Cloud-forest wildlife without guaranteed sightings | Product catalog | Link specialist birding and bear content to MBW.
MT034 | phase_2 | Medium | create | itinerary | travel_planning | en | /mindo-itinerary-one-day/ | /es/itinerario-mindo-un-dia/ | One-Day Mindo Itinerary | one day in Mindo itinerary | itinerario Mindo un día | informational_commercial | middle | Multiple active products | mixed_active | Build your one-day plan | See day trips | /mindo-day-trips/ ¦ /things-to-do-in-mindo/ ¦ /activities/ | https://mindobirdwatching.com/mindo-day-tour-from-quito/ | Article ¦ ItemList ¦ FAQPage ¦ BreadcrumbList | itinerary | itinerary | Morning-to-evening visual sequence | Product catalog and GSC day-trip demand | Provide modular options rather than claiming all activities fit one day.
MT034 | phase_2 | Medium | create | itinerary | travel_planning | es | /es/itinerario-mindo-un-dia/ | /mindo-itinerary-one-day/ | Itinerario de un Día en Mindo | itinerario Mindo un día | one day in Mindo itinerary | informational_commercial | middle | Multiple active products | mixed_active | Build your one-day plan | See day trips | /mindo-day-trips/ ¦ /things-to-do-in-mindo/ ¦ /activities/ | https://mindobirdwatching.com/mindo-day-tour-from-quito/ | Article ¦ ItemList ¦ FAQPage ¦ BreadcrumbList | itinerary | itinerary | Morning-to-evening visual sequence | Product catalog and GSC day-trip demand | Provide modular options rather than claiming all activities fit one day.
MT035 | phase_2 | Medium | create | itinerary | travel_planning | en | /mindo-itinerary-two-days/ | /es/itinerario-mindo-dos-dias/ | Two-Day Mindo Itinerary | two days in Mindo itinerary | itinerario Mindo dos días | informational_commercial | middle | Multiple active products | mixed_active | Build your two-day plan | Request private planning | /mindo-itinerary-one-day/ ¦ /private-tours-mindo/ ¦ /mindo-travel-guide/ | https://mindobirdwatching.com/ | Article ¦ ItemList ¦ FAQPage ¦ BreadcrumbList | itinerary | itinerary | Two-day activity sequence with rest time | Product catalog | Keep lodging recommendations generic unless verified.
MT035 | phase_2 | Medium | create | itinerary | travel_planning | es | /es/itinerario-mindo-dos-dias/ | /mindo-itinerary-two-days/ | Itinerario de Dos Días en Mindo | itinerario Mindo dos días | two days in Mindo itinerary | informational_commercial | middle | Multiple active products | mixed_active | Build your two-day plan | Request private planning | /mindo-itinerary-one-day/ ¦ /private-tours-mindo/ ¦ /mindo-travel-guide/ | https://mindobirdwatching.com/ | Article ¦ ItemList ¦ FAQPage ¦ BreadcrumbList | itinerary | itinerary | Two-day activity sequence with rest time | Product catalog | Keep lodging recommendations generic unless verified.
MT036 | phase_2 | Medium | create | audience_guide | family | en | /family-things-to-do-mindo/ | /es/actividades-en-mindo-con-ninos/ | Family Things to Do in Mindo | family things to do in Mindo | actividades en Mindo con niños | informational_commercial | middle | MBW011-MBW015 ¦ Selected active activities | active | Compare family activities | Request a private plan | /activities/butterfly-garden-mindo/ ¦ /activities/chocolate-tour-mindo/ ¦ /private-tours-mindo/ | https://mindobirdwatching.com/activities/ | Article ¦ ItemList ¦ FAQPage ¦ BreadcrumbList | audience_guide | audience_guide | Family-friendly activity montage | Product catalog | Do not assign age limits without verified operator rules.
MT036 | phase_2 | Medium | create | audience_guide | family | es | /es/actividades-en-mindo-con-ninos/ | /family-things-to-do-mindo/ | Actividades en Mindo con Niños | actividades en Mindo con niños | family things to do in Mindo | informational_commercial | middle | MBW011-MBW015 ¦ Selected active activities | active | Compare family activities | Request a private plan | /activities/butterfly-garden-mindo/ ¦ /activities/chocolate-tour-mindo/ ¦ /private-tours-mindo/ | https://mindobirdwatching.com/activities/ | Article ¦ ItemList ¦ FAQPage ¦ BreadcrumbList | audience_guide | audience_guide | Family-friendly activity montage | Product catalog | Do not assign age limits without verified operator rules.
MT037 | phase_2 | Medium | create | attraction_guide | waterfalls | en | /activities/mindo-tarabita-cable-car/ | /es/actividades/tarabita-de-mindo/ | Mindo Tarabita Cable Car | Mindo tarabita cable car | tarabita Mindo | informational_commercial | middle | MBW013 | active_related_product | Plan a waterfall visit | See guided waterfall tours | /activities/mindo-waterfall-hike/ ¦ /mindo-day-trips/ ¦ /things-to-do-in-mindo/ | https://mindobirdwatching.com/activities/ | TouristAttraction ¦ FAQPage ¦ BreadcrumbList | attraction_guide | attraction_guide | Tarabita over forested valley | MindoTours GSC queries and waterfall product | Verify current entrance and operating details before publication.
MT037 | phase_2 | Medium | create | attraction_guide | waterfalls | es | /es/actividades/tarabita-de-mindo/ | /activities/mindo-tarabita-cable-car/ | Tarabita de Mindo | tarabita Mindo | Mindo tarabita cable car | informational_commercial | middle | MBW013 | active_related_product | Plan a waterfall visit | See guided waterfall tours | /activities/mindo-waterfall-hike/ ¦ /mindo-day-trips/ ¦ /things-to-do-in-mindo/ | https://mindobirdwatching.com/activities/ | TouristAttraction ¦ FAQPage ¦ BreadcrumbList | attraction_guide | attraction_guide | Tarabita over forested valley | MindoTours GSC queries and waterfall product | Verify current entrance and operating details before publication.
MT038 | phase_3 | Hold | hold_for_product_approval | activity_page | specialty_wildlife | en | /activities/private-insect-macro-wildlife-search/ | /es/actividades/busqueda-privada-insectos-macrofauna/ | Private Insect and Macro Wildlife Search | Mindo insect tour | tour de insectos Mindo | commercial | bottom | ACT021 | new_specialty_activity_needs_review | Request review | Explore wildlife tours | /mindo-wildlife-nature-tours/ ¦ /private-tours-mindo/ ¦ /activities/night-walk-mindo/ | https://mindobirdwatching.com/activities/private-insect-macro-wildlife-search/ | Product ¦ TouristAttraction ¦ FAQPage ¦ BreadcrumbList | activity_wildlife | activity_page | Macro insect photography with placeholder | Product catalog | Do not publish until product review and Stripe IDs are complete.
MT038 | phase_3 | Hold | hold_for_product_approval | activity_page | specialty_wildlife | es | /es/actividades/busqueda-privada-insectos-macrofauna/ | /activities/private-insect-macro-wildlife-search/ | Búsqueda Privada de Insectos y Macrofauna | tour de insectos Mindo | Mindo insect tour | commercial | bottom | ACT021 | new_specialty_activity_needs_review | Request review | Explore wildlife tours | /mindo-wildlife-nature-tours/ ¦ /private-tours-mindo/ ¦ /activities/night-walk-mindo/ | https://mindobirdwatching.com/activities/private-insect-macro-wildlife-search/ | Product ¦ TouristAttraction ¦ FAQPage ¦ BreadcrumbList | activity_wildlife | activity_page | Macro insect photography with placeholder | Product catalog | Do not publish until product review and Stripe IDs are complete.
MT039 | phase_3 | Hold | hold_for_product_approval | activity_page | adventure | en | /activities/sky-bike-mindo/ | /es/actividades/bicicleta-extrema-mindo/ | Sky Bike in Mindo | sky bike Mindo | bicicleta extrema Mindo | commercial | bottom | ACT019 | new_activity_needs_review | Request review | Compare adventures | /mindo-adventure-tours/ ¦ /activities/ |  | Product ¦ TouristAttraction ¦ FAQPage ¦ BreadcrumbList | activity_adventure | activity_page | Sky bike placeholder | Product catalog | Do not publish until product details and accounting status are approved.
MT039 | phase_3 | Hold | hold_for_product_approval | activity_page | adventure | es | /es/actividades/bicicleta-extrema-mindo/ | /activities/sky-bike-mindo/ | Bicicleta Extrema en Mindo | bicicleta extrema Mindo | sky bike Mindo | commercial | bottom | ACT019 | new_activity_needs_review | Request review | Compare adventures | /mindo-adventure-tours/ ¦ /activities/ |  | Product ¦ TouristAttraction ¦ FAQPage ¦ BreadcrumbList | activity_adventure | activity_page | Sky bike placeholder | Product catalog | Do not publish until product details and accounting status are approved.
MT040 | phase_3 | Hold | hold_for_product_approval | activity_page | adventure | en | /activities/extreme-swing-mindo/ | /es/actividades/columpio-extremo-mindo/ | Extreme Swing in Mindo | extreme swing Mindo | columpio extremo Mindo | commercial | bottom | ACT018 | new_activity_needs_review | Request review | Compare adventures | /mindo-adventure-tours/ ¦ /activities/ |  | Product ¦ TouristAttraction ¦ FAQPage ¦ BreadcrumbList | activity_adventure | activity_page | Extreme swing placeholder | Product catalog | Do not publish until product details and accounting status are approved.
MT040 | phase_3 | Hold | hold_for_product_approval | activity_page | adventure | es | /es/actividades/columpio-extremo-mindo/ | /activities/extreme-swing-mindo/ | Columpio Extremo en Mindo | columpio extremo Mindo | extreme swing Mindo | commercial | bottom | ACT018 | new_activity_needs_review | Request review | Compare adventures | /mindo-adventure-tours/ ¦ /activities/ |  | Product ¦ TouristAttraction ¦ FAQPage ¦ BreadcrumbList | activity_adventure | activity_page | Extreme swing placeholder | Product catalog | Do not publish until product details and accounting status are approved.
MT041 | phase_3 | Hold | hold_for_product_approval | activity_page | adventure | en | /activities/sky-ride-mindo/ | /es/actividades/sky-ride-mindo/ | Sky Ride in Mindo | sky ride Mindo | sky ride Mindo | commercial | bottom | ACT020 | new_activity_needs_review | Request review | Compare adventures | /mindo-adventure-tours/ ¦ /activities/ |  | Product ¦ TouristAttraction ¦ FAQPage ¦ BreadcrumbList | activity_adventure | activity_page | Sky ride placeholder | Product catalog | Product flags conflict; hold publication until reviewed and confirmed active.
MT041 | phase_3 | Hold | hold_for_product_approval | activity_page | adventure | es | /es/actividades/sky-ride-mindo/ | /activities/sky-ride-mindo/ | Sky Ride en Mindo | sky ride Mindo | sky ride Mindo | commercial | bottom | ACT020 | new_activity_needs_review | Request review | Compare adventures | /mindo-adventure-tours/ ¦ /activities/ |  | Product ¦ TouristAttraction ¦ FAQPage ¦ BreadcrumbList | activity_adventure | activity_page | Sky ride placeholder | Product catalog | Product flags conflict; hold publication until reviewed and confirmed active.